This plan is to influence the sector to actively promote ‘Women in Sport’, ‘Disability in Sport’ and ‘racial inclusion’ over the course of two years to March 2026.  The Engagement & Delivery Plan will be further developed by and led by the Sports, Culture & Integrity Team, and will be actioned by programmes and staff across the organisation.

Background – Strategic Context:

Sport NI’s Corporate Plan 2021-26 ‘The Power of Sport’ targets sustained participation in sport and activity generally, and specifically from under-represented groups, contributing to improving physical activity in communities.

While, prior to the pandemic, we were seeing improvements in terms of the percentage of people who were participating in sport and physical activity, (The NI Continuous Household Survey 2020-21 notes a 3% rise in overall sports participation numbers to 59%), barriers clearly still exist for many in our society.  Challenges remain for people with a disability, women and girls, older people, carers, ethnically diverse communities and those from the LGBTQ+ community.  Whilst we have seen an increase in the support for, and the profile of, women in sport and those with a disability, there is much still to do which we aim to address through this corporate plan.  Consequently, the participation rates for these groups remain significantly below the general population rates for participation in sport and physical activity.

In terms of scale and its impact on society, it is fair to say that one particular demographic stands out. The under-representation of women and girls has long been recognised as one of the most significant problems within sport.

Current Context:

Women and Girls in Sport

In Northern Ireland, Women’s participation in sport is significantly lower than men.  In 2021/22, The Continuous Household Survey recorded that 48% of adults had participated in sport at least once within the last year (excluding walking), while 40% had participated in sport over the last 4 weeks. Females were less likely to have taken part in sport at least once within the last year than males (40% and 55% respectively).

Girls are not meeting their physical activity guidelines.  Fewer primary school girls (16%) participate in physical activity than boys (25%).  Post-primary the gap widens to girls at 10% compared with boys (22%).  The gap widens as children get older.  Female 16-year-olds remain the group with by far the lowest level of physical activity.  Whilst at age 10/11, there is virtually no gender difference between females and males in that respect, at 16, young men are much more physically active than young women (Kids Life & Times Survey and Young People’s Life & Times Surveys 2023)

From the baselines established in April 2023 as part of the ‘Sport Systems Investment – Governing Bodies’, 32.9% of coaches are females, 43.2% of volunteers are females and 28.9% of officials are females.  Research consistently identifies that the percentage representation of women within the coaching workforce reduces as the level of the pathway increases, and this is mirrored by higher levels of female drop-off within coach education as the levels of qualification progress.

Disability in Sport

One in four people in Northern Ireland has a disability or long-term health condition. This equates to approx. 463,000 people or notable 24.3% of the population (2021 NI Census). With that said, participation in sport in Northern Ireland is significantly lower for those with a disability. Disabled people in Northern Ireland remain half as likely to participate in sport and active recreation as non-disabled people (DSNI strategic plan 2020-2024).

Findings from the Continuous Household Survey 2022-2023 (NISRA) recorded that adults with a disability were less likely to participate in sport in the previous year (26%) compared to adults without a disability (56%). People with disabilities in Northern Ireland also have the lowest sport participation rates compared with other jurisdictions in the UK and Ireland. This is evident for the younger generation with a disability who are failing to meet their physical activity guidelines. According to the 2019 Young Person’s Behaviour and Attitudes Survey, young people who have a disability are less likely (54%) to participate in 2 hours or more of school PE lessons, compared to young people without a disability (64%).

The gap between disabled and non-disabled members of sports clubs is also widening. The 2019 Sport NI Club survey reported that 3% of 128,587 club members were people with disabilities. Disabled people are significantly less likely to be a member of a sports club or organisation, i.e. 14% of disabled people compared to 27% of non-disabled people (Experience of Sport in Northern Ireland -findings from the Continuous Household Survey 2018/19).

Research findings from the Sport NI ‘Sport Systems Investment – Governing Bodies’ programme (2023-2024) identifies that the representation of disability within club membership, coaching workforce, officials, and volunteers is significantly lower than those without a disability. For example, of all club members recorded within this investment period - 433,131 across 36 sports, only 1,916 were disabled club members. It is evident that sporting organisations require an improvement in their data and monitoring collection systems notably for their disabled members. An increased education of disability in sport is required to the wider sports sector as well as a broader awareness of the evidenced disability ‘gap’ and the importance of capturing and monitoring disability data for their sport.

The reality remains that opportunities for disabled people to participate in sport and active recreation in Northern Ireland are still not being provided on the scale required to give people with disabilities the same opportunities as non-disabled people to live a full, active, and healthy lifestyle (DSNI 2020-2024 Strategic Plan).

Racial Inclusion in Sport

Sport Northern Ireland alongside UK Sport, Sport England, sportscotland and Sport Wales are working together to tackle racism and racial inequalities in sport in their home countries and across the UK.

In 2020, the murder of George Floyd was a catalyst for the five Sports Councils responsible for investing in and growing sport across the UK, to come together to explore racial inequalities in sport and to look at how reflective our sporting system is of UK society.  This led to establishing the Tackling Racism and Racial Inequality in Sport Review (TRARIIS).  This was to help better understand if the Councils were doing enough to understand the context and tackle the issues involved.

The findings make clear that racism and racial inequalities still exist within sport in the UK and that there are longstanding issues, which have resulted in ethnically diverse communities being consistently disadvantaged.  The review also highlighted the detrimental impact that this has had on individuals, leading to mistrust and exclusion and makes clear areas where we must see change.

While recognising that this process will take time, the Councils are determined to learn from the review.  The aim is to bring transformational change across sport, harnessing its huge power to drive equality and ensuring that all parts of the system are fair, welcoming, inclusive, and diverse, so that people have positive experiences at every level.  The Councils have agreed some initial overarching commitments that all five organisations will work on together ensuring that they are aligned to their individual strategies.  Each Sports Council is working to develop their own specific plans to further deliver on the TRARIIS commitments, considering their own local contexts and remits whilst addressing the recommendations from the review.  Sport NI’s commitment to this is reflected in this Engagement and Delivery Plan.

Sport NI launched the ‘Moving to Inclusion’ Framework, toolkit and resources developed in conjunction with the Sports Councils Equality Group (SCEG), to promote EDI with their stakeholders and assist them as they seek to make organisations more diverse and inclusive.  The framework, toolkit and resources were launched to the NI sector on 9 February 2024 - https://movingtoinclusion.co.uk/.  The on-line hub is an initiative by the UK Sports Councils to provide support for EDI to sport and physical activity organisations – with the aim of moving towards a more diverse, inclusive and socially responsible sector.

Next Steps

For this plan to be effective, Sport NI will need to work closely with relevant external groups and communities, as well as internally across teams and investment strands, to identify potential solutions.  The plan is intended to support the wider sports sector to understand and recognise the issues and collectively bring about change.

| Pillar | Action Plan Objective | Action Plan Activity |
| --- | --- | --- |
| LEADERSHIP (joint actions) | Promoting females, people with a disability and people from ethnic diverse communities in decision making positions in sport - to deliver equitable representation for sports to achieve through current investment. Promote workforce opportunities for females, people with a disability and people from ethnic diverse communities to progress in sport i.e. coaches, officials, volunteers - to broaden the base. | Establish investment resources, partners and programmes required to deliver desired changes |
|  |  | Engage with sports to increase awareness of imbalance. |
|  |  | Ensure investment is focused on creating opportunities. |  |
|  |  | Measure progress at different intervals. |  |
|  |  | Monitor impact highlighting strong progress amongst particular sports |  |
| Women In Sport | Women in Sport | Establish investment resources, partners and programmes required to deliver desired changes |  |
| Racial Inclusion | Racial Inclusion | Engage with sports to increase awareness of imbalance. |  |
|  | Disability | Engage with sports to increase awareness of imbalance. |  |
| VISIBILITY AND ADVOCACY (Joint Actions) | Research that tracks trends re levels of participation, and underlying factors re female, people with a disability and people from ethnic diverse communities. | •Monitor awareness of gender, disability and racial inclusion gap in sport |  |
|  | Disability | Engage with sector to understand their research/insight needs |  |
|  | Racial Inclusion | Map research ecosystem - Share insights and research on regular basis with Sport NI commentary |  |
| Women In Sport | Campaign to increase the visibility of Women and Girls in sport and inspire Women and Girls to find their sport | Measure the impact of campaign at the completion of each phase of campaign |  |
| Disability | Communications & Advocacy interventions to increase visibility of people with a disability in sport and inspire those with a disability to find their sport. | Production and/or dissemination of high quality articles, publications, case studies which promote good practice associated with Sport NI's Disability Mainstreaming Policy. |  |
| Racial Inclusion | Communications & Advocacy interventions to increase visibility of people from ethnic minorities in sport and inspire those from ethnic minorities to find their sport. | Establish a network of partners for advocacy. |  |
|  |  | Production and/or dissemination of high quality articles, publications, case studies which promote good practice |  |
| PARTICIPATION (Joint Actions) | Focused investment to increase engagement in sport and physical activity among women and girls, disabled people and people from ethnically diverse communities. | Engage with peers and partners to shape investment |  |
|  |  | Track impact, share best practice and innovations |  |
| Women In Sport | Women In Sport | Deliver ring fenced investment for women and girls in sport |  |
| Disability | Disability | Deliver focused investment for people with a disability in sport |  |
| Racial Inclusion | Racial Inclusion | Potential Sported/CSN type business case |  |
|  | Provide structured support to Governing Bodies of Sport, mainstream sports clubs, and community organisations to identify and remove barriers and provide high quality sport and physical activity opportunities for females, people with a disability and people from ethnic diverse communities. | Track governing body membership data |  |
| Disability | Disability | Collate info on interventions by sports/clubs - showcase best practice |  |
| Racial Inclusion | Racial Inclusion | Provide tool-kit to review provision and club culture and resources to enhance the experience ethnically diverse communities in sport. |  |
| SPORTING FOUNDATIONS (Joint Actions) | Investment in infrastructure to support greater participation for females, people with a disability, and people from ethnic diverse communities e.g. changing facilities, accessible facilities etc. | Develop an understanding of how to make facilities more reflective of the needs of females, people withh disabilities and for people from ethnically diverse backgrounds |  |
| Disability | Disability | Build and share understanding of how to make infrastructure more reflective of needs of those with a disability. |  |
| Women In Sport | Partnership with Education and Sports to promote health and wellbeing alongside sport and physical activity in young girls especially teenagers | A.Engage with Education and other stakeholders to build awareness of the gap and it's impact into later life |  |
|  |  | B.Create coalition of partners |  |
|  |  | C.Deliver interventions via training, campaigns, invesment initiatives |  |
|  |  | D.Track progress through regular research |  |